## Sheet1
Sprint 1 Backlog Monday 12 March – 26 March 2018

Backlog Item	Story Points	Responsible	Status	Original Est.	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day7	Day 8	Day 9	Day 10
Story #1 – Get set up with necessary infrastructure	4			4
Create RDS MySQL instance and connect to it via MySQL workbench	1	Fatima	Completed (Day1)	1	1	0	0	0	0	0	0	0	0
Create Trello account, add group members	0.5	Orla	Completed (Day1)	0.5	0.5	0	0	0	0	0	0	0	0		Sprint 1 Burndown
Create GitHub repository for this product	0.5	Robert	Completed (Day1)	0.5	0.5	0	0	0	0	0	0	0	0
Project template using PyScaffold and push to GitHub	1	Orla	Completed (Day1)	1	1	0	0	0	0	0	0	0	0
Create Amazon ec2 instance, install Anaconda on it	1	Orla	Completed (Day1)	1	1	0	0	0	0	0	0	0	0
Story #2 – Scrape Dublin Bikes Data	28			28
Create a Python script to query the JCD API	5	Group	Completed (Day2)	5	0	0.5	0	0	0	0	0	0	0	0
Connect to RDS using python scraper	5	Group	Completed (Day2)	5	0	4	0	1	0	0	0	0	0	0
Store the data in correct format (i.e. in a dataframe) using web scraper	5	Group	Completed (Day2)	5	0	4	0	1	0	0	0	0	0	0
Create a table in RDS to store dynamic data and start saving down the data	3	Group	Completed (Day3)	3	0	2.5	0	0.5	0	0	0	0	0	0
Create a table in RDS to store static data such as address of stations	2	Group	Completed (Day3)	2	0	0	2	0	0	0	0	0	0	0
Write a console script to run this package	1	Orla	Completed (Day3)	1	0	0	1	0	0	0	0	0	0	0
Get the package installed on EC2 and start scraping data every 5 minutes	2	Robert	Completed (Day3)	2	0	0	2	0	0	0	0	0	0	0
User Story #3 – Scrape Weather Data	4			4
Get a key for the OpenWeather Maps API	1	Robert	Completed (Day4)	1	0	0	0	1	0	0	0	0	0	0
Practice using this API by obtaining real time weather information	1	Robert	Completed (Day4)	1	0	0	0	1	0	0	0	0	0	0
Create a table to store the most recent weather data	1	Group	Completed (Day4)	1	0	0	0	1	0	0	0	0	0	0
Link weather table to dynamic Dublin bikes table (for ease of analysis later)	1	Group	Completed (Day4)	1	0	0	0	1	0	0	0	0	0	0
User Story #4 – Create Basic Web app	7			7
Create Basic Flask App	2	Robert	Completed (Day 6)	2	0	0	0	0	0	1.5	0	0	0	0
Add Google map to web page	2	Fatima	Completed (Day6)	2	0	0	0	0	0	1	0	0	0	0
Do a mock up of final website layout	2	Group	NOT COMPLETED	2	0	0	0	0	0	0	0	0
Add basic extras to the web page such as footers etc.	1	Fatima	Completed (Day6)	1	0	0	0	0	0	1	0	0	0	0
User Story #5 – Display Position of Stations on Map	7			7
Add circles of varying sizes to Google Maps	3	Group	Completed (Day 7)	3	0	0	0	0	0	0	1	0	0	0
Try to read the positions of the stations from Amazon RDS	2	Orla	NOT COMPLETED	2	0	0	0	0	0	0	0	0
Store the locations of the stations in JSON format	1	Orla	Completed (Day9)	1	0	0	0	0	0	0	0	0	1	0
Display the stations by reading this JSON object	1	Robert	Completed (Day9)	1	0	0	0	0	0	0	0	0	1	0
Actual Hours Remaining				50	46	35	30	23.5	23.5	20	19	19	18	18
Ideal Hours Remaining	50			50	45	40	35	30	25	20	15	10	5	0