## Sheet1
Sprint 2 Backlog Monday 26 March – 9 April 2018

Backlog Item	Story Points	Responsible	Status	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5 (Good Friday)	Day 6(Easter Monday)	Day 7	Day 8	Day 9	Day 10
Story #1: Basic Information on click of a station	14		Completion Date	14
Get a basic info window displaying on click of each station	3	Orla	Day 8 – 4 April	3	0	0	0	0	0	0	0	3	0	0
Display static information (e.g.name) of a station in info window	3	Fatima	Day 9 – 5 April	3	0	0	0	0	0	0	0	0	3	0	Sprint 2 Burndown
Display dynamic information (availability) of a station in info window	5	Group	Day 9 – 5 April	5	0	0	0	0	0	0	0	0	5	0
Make Info Windows disappear on click of another station	3	Group	Day4 – 29 March	3	0	0	0	3	0	0	0	0	0	0

Story #2: Reduce wait time of our application	10			10
Write station locations to JSON file as temporary fix to increase speed	2	Orla	Day 3 – 28 March	2	0	0	2	0	0	0	0	0	0	0
Edit scraper to make new table of static data in a local .db fiile	5	Group	Day 9 – 5 April	5	0	0	0	0	0	0	0	0	5	0
Edit weather.html so that it displays the markers by reading local db file	3	Group	Day 9 – 5 April	3	0	0	0	0	0	0	0	0	3	0

Story #3 : Availability chart by rain for each station	13			13
Look into overall availability trends using df.resample	3	Group	Day 10 – 6 April	3	0	0	0	0	0	0	0	0	3
Parse the data into availability during rain & no rain (2 extra columns)	5	Group	Day 10 – 6 April	5	0	0	0	0	0	0	0	0	5
Plot this data on a bar plot using pandas	5	Group	Day 10 – 6 April	5	0	0	0	0	0	0	0	0	5

Story #4 : Fix issues with scraper when they arise	7			7
Scraper down at start of sprint 2 – determine cause of the problem	2	Group	Day 2 – 27 March	2	0	2	0	0	0	0	0	0	0	0
Add appropriate try/except blocks to catch these errors in future	2	Group	Day 2 – 27 March	2	0	2	0	0	0	0	0	0	0	0
Write exceptions from scraper to a file & the time they occurred	2	Group	Day 9 – 5 April	2	0	0	0	0	0	0	0	0	2	0
Tidy up scraper file (add comments and have less code in ‘main’)	1	Orla	NOT COMPLETED	1	0	0	0	0	0	0	0	0

Story #5 : Miscellaneous	15			15
Make our keys hidden	2	Fatima	NOT COMPLETED	2	0	0	0	0	0	0	0	0
Display real time weather information on the web app	2	Robert	NOT COMPLETED	2	0	0	0	0	0	0	0	0
Ensure the web app can run on the instance	1	Orla	Day 10 – 6 April	1	0	0	0	0	0	0	0	0	1
Make our code more readable (use jquery instead of XMLHttp)	3	Group	NOT COMPLETED	3	0	0	0	0	0	0	0	0
Reconsider the current package structure of our project	2	Group	Completed (Day 7)	2	0	0	0	0	0	0	2	0	0	0
Do Python Unit Tests of Code we have so far	5	Orla	NOT COMPLETED	5	0	0	0	0	0	0	0	0
Total				59	0	4	2	3	0	0	2	3	18	14
Actual Hours Remaining				59	59	55	53	50	50	50	48	45	27	13
Ideal Hours Remaining				59	53.1	47.2	41.3	35.4	29.5	23.6	17.7	11.8	5.9	0