## Sheet1
Sprint 3 Backlog Monday 9 April – 20 April 2018

Backlog Item	Story Points	Responsible	Completion Date	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10
Story #1: Display pie chart of availability (Google Charts)	8			8
Display any basic Google chart on click of a station	3	Group	Day 1 – 9 April	3	3	0	0	0	0	0	0	0	0
Display a pie chart with data relevant to our application	5	Group	Day 2 –10 April	5	0	5	0	0	0	0	0	0	0	0	Sprint 3 Burndown

Story #2: Display availability by rain chart (Google Charts)	15			15
Parse the data to obtain availability (by rain/no rain) and time	5	Group	Day 5 – 13 April	5	0	0	0	0	5	0	0	0	0	0
Make a Flask URL and store this data in a URL for each station	2	Group	Day 5 – 13 April	2	0	0	0	0	2	0	0	0	0	0
Display a basic bar chart on click of a station with hard coded values (for now!)	3	Group	Day 5 – 13 April	3	0	0	0	0	3	0	0	0	0	0
Populate the bar chart by reading from the Flask URL for that station	5	Group	Day 5 – 13 April	5	0	0	0	0	5	0	0	0	0	0

Story #3 : Make a model to predict bike availability	13			13
Consider what features to include in the model and learn about pickle	2	Robert	Day 6 – 16 April	2	0	0	0	0	0	2	0	0	0	0
Use pickle to create a model for each station for each hour for each day	8	Group	Day 7 – 17 April	8	0	0	0	0	0	0	8	0	0	0
Test the models with data for 1 station to ensure reasonable results	3	Group	Day 7 – 17 April	3	0	0	0	0	0	0	3	0	0	0

Story #4 : Integrate model with website	20			20
Make drop downs on the web page to select time and day	5	Orla	Day 6 – 16 April	5	0	0	0	0	0	5	0	0	0	0
(OPTIONAL) Make a submit button on the main html page (to get prediction)	2	Fatima	NOT COMPLETED	2	0	0	0	0	0	0	0	0
Make a Flask URL in views.py to hold the model for that station	5	Group	Day 9- 19 April	5	0	0	0	0	0	0	0	0	5	0
Edit the main html file to access these predictions on click of submit	8	Group	Day 10- 20 April	8	0	0	0	0	0	0	0	0	8

Story #5: Miscellaneous	12			12
Display real time weather information and time on the web app	3	Orla	Day 6 – 16 April	3	0	0	0	0	0	3	0	0	0	0
Do Python Unit Tests of Code we have so far	5	Orla	Day 10- 20 April	5	0	0	0	0	0	0	0	0	5
Fix issues with scraper if they arise	2	Group	Day 8 – 18 April	2	0	0	0	0	0	0	0	2	0	0
Tidy up website, make legend for map etc.	2	Fatima	Day 9- 20 April	2	0	0	0	0	0	0	0	0	2	0
Total				68	3	5	0	0	15	10	11	2	7	13

Actual Hours Remaining				68	65	60	60	60	45	35	24	22	15	2
Ideal Hours Remaining				68	61.2	54.4	47.6	40.8	34	27.2	20.4	13.6	6.8	0